## Benefits Plan
Benefits Realization Plan
One row per benefit, not one per project. A benefit with no named owner and no measure is a wish, so both columns are mandatory.
ID | Project | Benefit | Type | Benefit owner | How it is measured | Baseline | Target | Actual to date | % realized | Measure from | Review date | Status
B-01 | Billing replatform | Invoice processing hours cut | Cash releasing | Controller | Hours logged to invoice processing per month | 1200 | 480 | 640 |  | 2026-12-01 | 2027-03-31 | On track
B-02 | Billing replatform | Legacy billing system retired | Cost avoidance | CIO | Annual license and hosting spend on legacy platform | 310000 | 0 | 310000 |  | 2027-01-31 | 2027-04-30 | Not started
B-03 | CRM migration | Churn reduced in mid market | Revenue | CRO | Rolling 12 month logo churn, mid market segment | 0.14 | 0.1 | 0.13 |  | 2027-02-01 | 2027-06-30 | At risk
B-04 | Warehouse analytics | Stock write off reduced | Cash releasing | COO | Quarterly write off as a share of inventory value | 0.031 | 0.018 | 0.028 |  | 2027-07-01 | 2027-10-31 | On track
B-05 | Data center exit | Audit findings closed | Non financial | CISO | Open high severity findings from the annual audit | 9 | 0 | 4 |  | 2027-01-15 | 2027-02-28 | On track
% realized measures movement from baseline toward target, so it works whether the benefit goes up (revenue) or down (churn, hours, write offs).
"Measure from" is the date the benefit can first be read, which is normally months after the project closes. That gap is where most benefits quietly die.

## Profile
Benefit profile
Fill one of these per material benefit before the business case is approved. If you cannot fill it in, the benefit is not real yet.
Field | Entry
Benefit ID | B-01
Description | Invoice processing hours cut by 60%
Type | Cash releasing / cost avoidance / revenue / non financial
Benefit owner (accountable) | Controller, not the project manager
Measure | Hours logged to invoice processing per month
Data source | Timesheet system, finance ops cost center
Baseline value and date | 1,200 hours per month, measured Q4 2025
Target value and date | 480 hours per month by 2027-03-31
Dependencies | Requires the legacy platform to be switched off
What could stop it | Volumes grow, or the team is not redeployed
Who signs it off as realized | CFO, at the post implementation review