## Dependency Matrix
Dependency Structure Matrix (DSM)
Read it row by row: put a 1 where the row item DEPENDS ON the column item. Marks above the diagonal are feedback loops and need attention first.
| Identity service | Payments API | Billing UI | Data migration | Partner sandbox | Reporting | Go live
Identity service
Payments API | 1
Billing UI | 1 | 1
Data migration | 1
Partner sandbox |  | 1
Reporting |  |  | 1 | 1
Go live |  |  | 1 | 1 | 1 | 1
Predecessors (row total)
Successors (column total)
The item with the highest successor count is your critical bottleneck: everything downstream waits on it. Sequence it first, and protect it.

## Dependency Log
Dependency log
The matrix shows the shape. The log carries the detail an owner can actually act on.
ID | Predecessor (must finish) | Successor (waits on it) | Type | Lag (days) | Owner | Needed by | Status
D-01 | Identity service | Payments API | FS | 0 | J. Okafor | 2026-08-14 | On track
D-02 | Payments API | Billing UI | FS | 5 | S. Patel | 2026-09-01 | At risk
D-03 | Identity service | Data migration | SS | 0 | A. Rivera | 2026-08-20 | On track
D-04 | Payments API | Partner sandbox | FS | 10 | External vendor | 2026-09-15 | Blocked
D-05 | Data migration | Reporting | FF | 0 | A. Rivera | 2026-10-01 | Not started
Type: FS = finish to start, SS = start to start, FF = finish to finish, SF = start to finish. Every dependency needs a single named owner on both sides.