## Portfolio
Project Portfolio Tracker
One row per project. The Dashboard tab reads this sheet, so keep the column order. Variance and health calculate themselves.
ID | Project | Owner | Sponsor | Strategic objective | Stage | RAG | Start | End | Budget | Actual to date | Forecast at completion | Variance | Priority score
P-01 | Billing replatform | S. Patel | CFO | Reduce cost to serve | Delivery | Amber | 2026-02-01 | 2026-11-30 | 1450000 | 820000 | 1560000 |  | 4.12
P-02 | CRM migration | A. Rivera | CRO | Grow retention | Delivery | Green | 2026-04-01 | 2027-01-31 | 890000 | 310000 | 880000 |  | 3.95
P-03 | Warehouse analytics | J. Okafor | COO | Improve margin | Planning | Green | 2026-09-01 | 2027-06-30 | 620000 | 40000 | 620000 |  | 3.5
P-04 | Partner portal | M. Lindqvist | CRO | Grow retention | Idea | Grey | 2027-01-01 | 2027-09-30 | 400000 | 0 | 400000 |  | 2.65
P-05 | Data center exit | J. Okafor | CIO | Reduce cost to serve | Delivery | Red | 2025-10-01 | 2026-12-31 | 2100000 | 1740000 | 2480000 |  | 3.7

## Dashboard
Portfolio dashboard
Every figure is a formula over the Portfolio tab. Nothing here is typed by hand.
Measure | Value
Projects in the portfolio
Total budget
Total forecast at completion
Portfolio variance
Spend to date
Budget consumed
Red projects
Amber projects
Green projects
Value at risk (red and amber forecast)
Spend by strategic objective
Strategic objective | Forecast spend | Share of portfolio
Reduce cost to serve
Grow retention
Improve margin
If an objective the board calls critical is carrying 5% of portfolio spend, the portfolio does not believe the strategy. That gap is the conversation.