## Scoring Matrix
Project Prioritization Matrix
Set the criteria weights in row 5 (they should total 100%). Score each project 1 to 5. The weighted score and rank calculate themselves.
Weights
Must total 100% | 30% | 25% | 15% | 20% | 10%
Project | Strategic fit | Financial return | Risk (5 = low risk) | Customer impact | Delivery confidence | Weighted score | Rank
Billing replatform | 5 | 4 | 3 | 4 | 3
CRM migration | 4 | 3 | 3 | 5 | 4
Warehouse analytics | 3 | 4 | 4 | 2 | 4
Partner portal | 2 | 2 | 3 | 3 | 5
Data center exit | 5 | 5 | 2 | 1 | 2
Mobile app refresh | 3 | 2 | 4 | 4 | 4
Score 1 to 5 against a written definition of what each score means, not on gut feel. Write the anchors down before anyone sees the project list.
Invert any criterion where high is bad. Risk is scored 5 = low risk here so that every column points the same way.

## Score Anchors
Score anchors
Agree these before scoring. They are what stops the loudest person in the room from winning.
Criterion | Score 1 | Score 5
Strategic fit | No line of sight to a stated objective | Directly delivers a board-level objective this year
Financial return | NPV negative or unquantified | NPV positive with payback inside 18 months
Risk (5 = low risk) | Unproven tech, no owner, external dependency | Known tech, named owner, no external dependency
Customer impact | Internal only, no customer notices | Fixes a top-three customer complaint
Delivery confidence | No team identified, estimate is a guess | Team named and available, estimate based on a similar delivery